## Sheet1
Related User Story | Task Description | Task Assigned | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
The user would want to delete images | Create delete functionality to handle delete for code behind | Janera | 6 | 6 | 5 | 5 | 0
The user would want to delete images | create tests to cover delete functionality | Anton/Janera | 8 | 8 | 7 | 4 | 0
The user would want to cancel and return to the homepage | Fix Cancel functionality to be connected back to the homepage | Anton | 1 | 1 | 0 | 0 | 0
The user would want to log-in | Create server side for authentication log in | Oumar | 13 | 10 | 7 | 4 | 1
| Estimate Totals |  | 28 | 25 | 19 | 13 | 1