## Sheet1
Related User Story | Task Description | Task Assigned | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
The user would want to delete images | Create delete functionality to handle delete for code behind | Janera | 6
The user would want to view image details | Create functionality to view image details for code behind | Oumar | 8
The user would want to cancel and return to the homepage | Fix Cancel functionality to be connected back to the homepage | Anton | 1
The user would want to log-in | Create server side for authentication log in | Janera/Oumar | 13
The user would want to upload images | Create server side for uploading images | Anton | 15
| Estimate Totals |  | 43 | 0 | 0 | 0 | 0