## Sheet1
Related User Story | Task Description | Task Assigned | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things… |  | 100 | 75 | 50 | 25 | 0
The user would want to upload images | Create Images class | Janera | 5 | 5 | 3 | 2 | 0
The user would want to upload images | Create UI for uploading images | Anton | 12
The user would want to upload images | Create UI to view all uploaded images | Oumar | 8 | 12 | 10 | 5 | 0
The user would want to upload images | Create Images Inventory | Oumar | 5 | 5 | 4 | 0 | 0
| Update Class Diagram | Janera | 3
| Estimate Totals |  | 133 | 87 | 60 | 30 | 0