## Sheet1
Related User Story | Task Description | Task Assigned | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
share all images I uploaded | Create UI to support share functionality | Anton/Oumar | 12 | 10 | 9 | 5 | 0
share all images I uploaded | Create Tests to cover new code Additions | Janera | 7 | 6 | 5 | 3 | 0
delete images | Update Delete Images to delete image on all pages | Anton | 6 | 6 | 5 | 4 | 0
documentation | Update UML Diagram | Oumar/Janera | 4 | 4 | 4 | 2 | 0
share all images I uploaded | Add Extra attribute to images | Anton/Oumar | 2 | 2 | 0 | 0 | 0
share all images I uploaded | Create public sharing feature | Anton | 10 | 9 | 7 | 4 | 0
share all images I uploaded | Create private sharing feature | Oumar | 10 | 9 | 6 | 4 | 0
share all images I uploaded | update AddImage page | Anton | 4 | 3 | 3 | 1 | 0
see all shared images I uploaded | update homepage | Oumar/Janera | 6 | 4 | 3 | 2 | 0
documentation | update use case diagram | Janera | 3 | 3 | 3 | 3 | 0
| Estimate Totals |  | 64 | 56 | 45 | 28 | 0